## full stack data scien
Full Stack Data Scientist Project Template
Captures the main points of a successful Data Science Project.
Scope the Project
Name | Subtasks | Description | Owner | Participants | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Cost | Completion Date
Preliminary Meeting | Stakeholder Intro,Detailed Expectation and Requirements,Questions from the Team,Schedule Project Launch Meeting | Understand stakeholder expectations | Project Manager | Data Engineer, Data Scientist, Machine Learning Engineer, Stakeholders | Done | 2025-01-17 | 2025-01-17 | 1 |  | 12 | 8 | 0 | 2025-01-17
Subitems | Name | Description | Status | Duration
| Stakeholder Intro | Introduce each stakeholder, and understand each individuals need and expectation for the project. | Working on it | 10
| Detailed Expectation and Requirements | Understand the request's what, where and how. (see comment for guiding questions) | Done | 15
| Questions from the Team | Allow team members to ask any outlying questions. | Done | 5
| Schedule Project Launch Meeting | Occurs after team has strategized and mapped out project. 3-5 days from Prelim. Meeting. | Done | 5
Strategizing | Data Engineering,Data Scientist,ML Engineer | Estimate, time, work, resources and cost. | Project Manager | Data Scientist, Data Engineer, Machine Learning Engineer | Done | 2025-01-18 | 2025-01-22 | 5 | Preliminary Meeting | 22 | 20 | 0 | 2025-01-17
Subitems | Name | Description | Status | Duration
| Data Engineering | Estimate cost and time to completion and record in "Data Pipeline and Visualization" | Done | 1.5
| Data Scientist | Estimate cost and time to completion and record in "ML Model Build and Training" | Done | 1.5
| ML Engineer | Estimate cost and time to completion and record in "ML Deployment and Wrap Up" | Done | 1.5
Project Kickoff Meeting | Showcase Timeline,Showcase Example End Product,Stakeholder Feedback,Establish Project Touchpoint Rhythm | Report back to stakeholders with complete estimated project plan | Project Manager | Stakeholders, Data Engineer, Data Scientist, Machine Learning Engineer | Done | 2025-01-23 | 2025-01-23 | 1 | Strategizing | 10 | 14 | 0 | 2025-01-17
Subitems | Name | Description | Status | Duration
| Showcase Timeline | Walk stakeholders through timeline and tasks, start to finish. | Done | 5
| Showcase Example End Product | If applicable, the team will present proposed end product example | Done | 5
| Stakeholder Feedback | Deep dive into details, timing, necessity and cost at stakeholder's behest. | Done | 15
| Establish Project Touchpoint Rhythm | Establish recurring meeting with team and stakeholders for project updates. Should be condusive to everyone's schedule | Done | 2
[6 empty] | 2025-01-17 | 2025-01-23 | [5 empty] | 2025-01-17
Data Pipelining and Visualization
Name | Subtasks | Description | Owner | Participants | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Cost | Completion Date
Create Data Pipeline |  | Deliverable: Functioning and self-refreshing pipeline. | Data Engineer | Data Scientist | Done | 2025-01-24 | 2025-02-06 | 14 | Project Kickoff Meeting | 50 | 46 | 0 | 2025-01-17
Project Status Touchpoint |  |  | Project Manager | Data Scientist, Machine Learning Engineer, Data Engineer, Stakeholders | Done | 2025-02-06 | 2025-02-06 | 0 |  | 0.5 | 0.5 | 0 | 2025-01-17
Data Monitoring and Visibility |  | Deliverable: Data in accessibly and readable format | Data Engineer |  | Done | 2025-02-07 | 2025-02-20 | 14 | Create Data Pipeline | 9 | 10 | 0 | 2025-01-17
Project Status Touchpoint |  |  | Project Manager | Data Scientist, Machine Learning Engineer, Data Engineer, Stakeholders | Done | 2025-02-20 | 2025-02-20 | 0 |  | 0.5 | 0.5 | 0 | 2025-01-17
[6 empty] | 2025-01-24 | 2025-02-20 | [5 empty] | 2025-01-17
ML Model Build and Training
Name | Subtasks | Description | Owner | Participants | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Cost | Completion Date
Build and Train Model |  | Deliverable: Trained and tested model ready for deployment | Data Scientist | Machine Learning Engineer | Done | 2025-02-21 | 2025-03-09 | 17 | Data Monitoring and Visibility | 60 | 62 | 0 | 2025-01-17
Project Status Touhpoint |  |  | Project Manager | Stakeholders, Data Scientist, Data Engineer, Machine Learning Engineer | Done | 2025-03-06 | 2025-03-06 | 0 |  | 0.5 | 0.5 | 0 | 2025-01-17
Evaluate Performance Metrics and Errors |  | Optimize where possible. Identify common data issues w/ Data Engineer | Data Scientist | Data Engineer | Done | 2025-03-10 | 2025-03-15 | 6 | Build and Train Model | 20 | 20 |  | 2025-01-17
[6 empty] | 2025-02-21 | 2025-03-15 | [5 empty] | 2025-01-17
ML Deployment and Wrap Up
Name | Subtasks | Description | Owner | Participants | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Cost | Completion Date
Containerize model and develop API |  | Deliverable: Containerized ML Solution and API | Machine Learning Engineer |  | Done | 2025-03-16 | 2025-03-28 | 13 | Evaluate Performance Metrics and Errors |  |  |  | 2025-01-17
Project Status Touchpoint |  | On the last touchpoint meeting, schedule delivery meeting | Project Manager | Stakeholders, Machine Learning Engineer, Data Scientist, Data Engineer | Done | 2025-03-20 | 2025-03-20 | 0 |  | 0.5 | 0.5 |  | 2025-01-17
Orchestrate and Connect to Data Pipeline |  | Deliverable: Operable link between Pipeline and ML Soultion | Machine Learning Engineer | Data Engineer, Data Scientist | Done | 2025-03-29 | 2025-04-04 | 7 | Containerize model and develop API |  | 0 |  | 2025-01-17
Soft Launch |  | Evaluate volunteer-user-to-finished-product interface | Machine Learning Engineer |  | Done | 2025-04-05 | 2025-04-07 | 3 | Orchestrate and Connect to Data Pipeline |  | 0 |  | 2025-01-17
Final Tweaking |  | Time allotted for error proofing | Project Manager | Data Scientist, Data Engineer, Machine Learning Engineer | Done | 2025-04-08 | 2025-04-12 | 5 | Soft Launch |  | 0 |  | 2025-01-17
[6 empty] | 2025-03-16 | 2025-04-12 | [5 empty] | 2025-01-17
Launch
Name | Subtasks | Description | Owner | Participants | Status | Timeline - Start | Timeline - End | Duration | Dependent On | Planned Effort | Effort Spent | Cost | Completion Date
Delivery Meeting | Demo/ Follow Along Instruction,Review Limitations/ Proper Use,Stakeholder Satisfaction |  | Project Manager | Stakeholders, Machine Learning Engineer, Data Engineer, Data Scientist | Done | 2025-04-13 | 2025-04-13 | 1 | Final Tweaking | 5 | 5 |  | 2025-01-17
Subitems | Name | Description | Status | Duration
| Demo/ Follow Along Instruction | Show stakeholders how to access and interface end product. | Done | 15
| Review Limitations/ Proper Use |  | Done | 5
| Stakeholder Satisfaction | Ensure stakeholders are completely satisfied with the end product. | Done | 10
Help Availability |  | The team is available to assist end product users | Project Manager | Data Engineer, Data Scientist, Machine Learning Engineer | Done |  |  | 9 | Delivery Meeting | 6 | 3 |  | 2025-01-17
[6 empty] | 2025-04-13 | 2025-04-13 | [5 empty] | 2025-01-17